## 2_1 Daily Progress
| 2. Work Status | [41 empty] | As of sep. 27, 2018
WORK AREA |  |  | UNIT | TOTAL QUANTITY | WORK DONE |  |  |  | WORK TO BE DONE | TARGET DATE | REMAINING DURATION | WORK VOL. TO BE DONE PER DAY | WORK PROGRESS OF THIS MONTH (AUG)
|  |  |  | (A) | LAST MTH (B1) | THIS MTH(B2) | SUM (B=B1+B2) | RATE (%) | (C = A - B) | (D) | (E) | (F = C / E) | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
Concrete Pouring | CEB | Lean | M3 | 136.1 | 113 | 94 | 207 | 152.1% | -70.9 |  |  | #DIV/0! | WORK PROGRESS OF THIS MONTH (AUG) 4: 4; WORK PROGRESS OF THIS MONTH (AUG) 8: 72; WORK PROGRESS OF THIS MONTH (AUG) 15: 8; WORK PROGRESS OF THIS MONTH (AUG) 25: 10 | CEB
|  | CON`C(ABOVE) | M3 | 642.6 | 0 | 0 | 0 | 0% | 642.6 |  |  | #DIV/0! | [31 empty] | CEB
|  | CON`C(UNDER) | M3 | 693.7 | 843 | 62 | 905 | 130.5% | -211.3 |  |  | #DIV/0! | WORK PROGRESS OF THIS MONTH (AUG) 8: 32; WORK PROGRESS OF THIS MONTH (AUG) 11: 30 | CEB
| Main BLDG | Lean | M3 | 766 | 275.5 | 4 | 279.5 | 36.49% | 486.5 |  |  | #DIV/0! | WORK PROGRESS OF THIS MONTH (AUG) 22: 4 | Main BLDG
|  | CON`C(ABOVE) | M3 | 106 | 0 | 0 | 0 | 0% | 106 |  |  | #DIV/0! | [31 empty] | Main BLDG
|  | CON`C(UNDER) | M3 | 4905 | 2197 | 290 | 2487 | 50.7% | 2418 |  |  | #DIV/0! | WORK PROGRESS OF THIS MONTH (AUG) 3: 70; WORK PROGRESS OF THIS MONTH (AUG) 7: 16; WORK PROGRESS OF THIS MONTH (AUG) 8: 18; WORK PROGRESS OF THIS MONTH (AUG) 10: 91; WORK PROGRESS OF THIS MONTH (AUG) 12: 65; WORK PROGRESS OF THIS MONTH (AUG) 15: 30 | Main BLDG
| GTG | Lean | M3 | 32 | 31 | 0 | 31 | 96.88% | 1 |  |  | #DIV/0! | [31 empty] | GTG
|  | CON`C(ABOVE) | M3 | 616 | 0 | 0 | 0 | 0% | 616 |  |  | #DIV/0! | [31 empty] | GTG
|  | CON`C(UNDER) | M3 | 160 | 0 | 0 | 0 | 0% | 160 |  |  | #DIV/0! | [31 empty] | GTG
| STG | Lean | M3 | 460.2 | 22 | 27 | 49 | 10.65% | 411.2 |  |  | #DIV/0! | WORK PROGRESS OF THIS MONTH (AUG) 25: 27 | STG
|  | CON`C(ABOVE) | M3 | 1166 | 0 | 0 | 0 | 0% | 1166 |  |  | #DIV/0! | [31 empty] | STG
|  | CON`C(UNDER) | M3 | 1496 | 0 | 842 | 842 | 56.28% | 654 |  |  | #DIV/0! | WORK PROGRESS OF THIS MONTH (AUG) 15: 842 | STG
| WTB | Lean | M3 | 128.0378 | 67.5 | 3 | 70.5 | 55.06% | 57.5378 |  |  | #DIV/0! | WORK PROGRESS OF THIS MONTH (AUG) 25: 3 | WTB
|  | CON`C(ABOVE) | M3 | 182.9532 | 0 | 0 | 0 | 0% | 182.9532 |  |  | #DIV/0! | [31 empty] | WTB
|  | CON`C(UNDER) | M3 | 688.9676 | 313 | 0 | 313 | 45.43% | 375.9676 |  |  | #DIV/0! | [31 empty] | WTB
| FGCB | Lean | M3 | 165.9 | 53 | 17 | 70 | 42.19% | 95.9 |  |  | #DIV/0! | WORK PROGRESS OF THIS MONTH (AUG) 22: 17 | FGCB
|  | CON`C(ABOVE) | M3 | 63.4 | 0 | 0 | 0 | 0% | 63.4 |  |  | #DIV/0! | [31 empty] | FGCB
|  | CON`C(UNDER) | M3 | 1052.3 | 229 | 15 | 244 | 23.19% | 808.3 |  |  | #DIV/0! | WORK PROGRESS OF THIS MONTH (AUG) 25: 15 | FGCB
| FGEB | Lean | M3 | 110.6 | 6 | 8 | 14 | 12.66% | 96.6 |  |  | #DIV/0! | WORK PROGRESS OF THIS MONTH (AUG) 8: 8 | FGEB
|  | CON`C(ABOVE) | M3 | 42.3 | 0 | 0 | 0 | 0% | 42.3 |  |  | #DIV/0! | [31 empty] | FGEB
|  | CON`C(UNDER) | M3 | 701.6 | 31.5 | 23 | 54.5 | 7.768% | 647.1 |  |  | #DIV/0! | WORK PROGRESS OF THIS MONTH (AUG) 15: 1; WORK PROGRESS OF THIS MONTH (AUG) 25: 22 | FGEB
| FWPB | Lean | M3 | 16.6 | 6 | 0 | 6 | 36.14% | 10.6 |  |  | #DIV/0! | [31 empty] | FWPB
|  | CON`C(ABOVE) | M3 | 22.5 | 0 | 8 | 8 | 35.56% | 14.5 |  |  | #DIV/0! | WORK PROGRESS OF THIS MONTH (AUG) 11: 8 | FWPB
|  | CON`C(UNDER) | M3 | 86.3 | 24 | 2 | 26 | 30.13% | 60.3 |  |  | #DIV/0! | WORK PROGRESS OF THIS MONTH (AUG) 22: 2 | FWPB
| DH S&ACB | Lean | M3 | 62 | 20 | 0 | 20 | 32.26% | 42 |  |  | #DIV/0! | [31 empty] | DH S&ACB
|  | CON`C(ABOVE) | M3 | 42.7 | 0 | 20 | 20 | 46.84% | 22.7 |  |  | #DIV/0! | WORK PROGRESS OF THIS MONTH (AUG) 22: 20 | DH S&ACB
|  | CON`C(UNDER) | M3 | 379.7 | 92 | 0 | 92 | 24.23% | 287.7 |  |  | #DIV/0! | [31 empty] | DH S&ACB
| Calrfied WPB | Lean | M3 | 25.8 | 11 | 0 | 11 | 42.64% | 14.8 |  |  | #DIV/0! | [31 empty] | Calrfied WPB
|  | CON`C(ABOVE) | M3 | 21.6 | 0 | 0 | 0 | 0% | 21.6 |  |  | #DIV/0! | [31 empty] | Calrfied WPB
|  | CON`C(UNDER) | M3 | 123.2 | 30 | 10 | 40 | 32.47% | 83.2 |  |  | #DIV/0! | WORK PROGRESS OF THIS MONTH (AUG) 12: 10 | Calrfied WPB
| Demi. Pump Building | Lean | M3 | 21.3 | 0 | 0 | 0 | 0% | 21.3 |  |  | #DIV/0! | [31 empty] | Demi. Pump Building
|  | CON`C(ABOVE) | M3 | 28.7 | 0 | 0 | 0 | 0% | 28.7 |  |  | #DIV/0! | [31 empty] | Demi. Pump Building
|  | CON`C(UNDER) | M3 | 104.4 | 4 | 22 | 26 | 24.9% | 78.4 |  |  | #DIV/0! | WORK PROGRESS OF THIS MONTH (AUG) 10: 16; WORK PROGRESS OF THIS MONTH (AUG) 22: 6 | Demi. Pump Building
| Switchyard Control Building | Lean | M3 | 21.3 | 9.5 | 0 | 9.5 | 44.6% | 11.8 |  |  | #DIV/0!
|  | CON`C(ABOVE) | M3 | 109.2 | 0 | 0 | 0 | 0% | 109.2 |  |  | #DIV/0!
|  | CON`C(UNDER) | M3 | 134.2 | 0 | 0 | 0 | 0% | 134.2 |  |  | #DIV/0!
| RWPB | Lean | M3 | 12.8 | 26 | 0 | 26 | 203.1% | 12.8 |  |  | #DIV/0! | [31 empty] | RWPB
|  | CON`C(ABOVE) | M3 | 13.8 | 0 | 0 | 0 | 0% | 13.8 |  |  | #DIV/0! | [31 empty] | RWPB
|  | CON`C(UNDER) | M3 | 72.2 | 26 | 8 | 34 | 47.09% | 72.2 |  |  | #DIV/0! | WORK PROGRESS OF THIS MONTH (AUG) 11: 8 | RWPB
FORM WORK | CEB | FAIR FACED FORM | M2 | 592.3 | 0 | 12 | 12 | 2.026% | 580.3 |  |  | #DIV/0! | WORK PROGRESS OF THIS MONTH (AUG) 7: 12 | CEB
|  | NORMAL FACED FORM | M2 | 1400.2 | 1660.34 | 572 | 2232.34 | 159.4% | -832.14 |  |  | #DIV/0! | WORK PROGRESS OF THIS MONTH (AUG) 6: 100; WORK PROGRESS OF THIS MONTH (AUG) 7: 250; WORK PROGRESS OF THIS MONTH (AUG) 8: 30; WORK PROGRESS OF THIS MONTH (AUG) 9: 30; WORK PROGRESS OF THIS MONTH (AUG) 10: 20; WORK PROGRESS OF THIS MONTH (AUG) 11: 20; WORK PROGRESS OF THIS MONTH (AUG) 12: 20; WORK PROGRESS OF THIS MONTH (AUG) 13: 20; WORK PROGRESS OF THIS MONTH (AUG) 18: 20; WORK PROGRESS OF THIS MONTH (AUG) 19: 20; WORK PROGRESS OF THIS MONTH (AUG) 20: 20; WORK PROGRESS OF THIS MONTH (AUG) 21: 15; WORK PROGRESS OF THIS MONTH (AUG) 22: 5; WORK PROGRESS OF THIS MONTH (AUG) 23: 1; WORK PROGRESS OF THIS MONTH (AUG) 24: 1 | CEB
| Main BLDG | FAIR FACED FORM | M2 | 665.4 | 0 | 0 | 0 | 0% | 665.4 |  |  | #DIV/0! | [31 empty] | Main BLDG
|  | NORMAL FACED FORM | M2 | 8856.5 | 2648.46 | 540 | 3188.46 | 36% | 5668.04 |  |  | #DIV/0! |  |  | 30 | 50 | 50 |  | 20 | 30 | 20 | 20 | 30 | 20 | 20 | 20 | 20 | 30 |  | 20 | 20 | 20 | 20 | 20 | 25 | 35 |  |  | 20 |  |  |  |  | Main BLDG
| GTG | FAIR FACED FORM | M2 | 125.5116 | 0 | 0 | 0 | 0% | 125.5116 |  |  | #DIV/0! | [31 empty] | GTG
|  | NORMAL FACED FORM | M2 | 120.72 | 32 | 279 | 311 | 257.6% | -190.28 |  |  | #DIV/0! | WORK PROGRESS OF THIS MONTH (AUG) 10: 50; WORK PROGRESS OF THIS MONTH (AUG) 11: 70; WORK PROGRESS OF THIS MONTH (AUG) 12: 5; WORK PROGRESS OF THIS MONTH (AUG) 13: 3; WORK PROGRESS OF THIS MONTH (AUG) 20: 1; WORK PROGRESS OF THIS MONTH (AUG) 21: 40; WORK PROGRESS OF THIS MONTH (AUG) 22: 20; WORK PROGRESS OF THIS MONTH (AUG) 23: 20; WORK PROGRESS OF THIS MONTH (AUG) 24: 20; WORK PROGRESS OF THIS MONTH (AUG) 25: 40; WORK PROGRESS OF THIS MONTH (AUG) 26: 10 | GTG
| STG | SYSTEM FORM | M2 | 981 | 10 | 220 | 230 | 23.45% | 751 |  |  | #DIV/0! | WORK PROGRESS OF THIS MONTH (AUG) 6: 100; WORK PROGRESS OF THIS MONTH (AUG) 7: 70; WORK PROGRESS OF THIS MONTH (AUG) 8: 20; WORK PROGRESS OF THIS MONTH (AUG) 9: 20; WORK PROGRESS OF THIS MONTH (AUG) 10: 10 | STG
|  | NORMAL FACED FORM | M2 | 473 | 8 | 8 | 16 | 3.383% | 457 |  |  | #DIV/0! | WORK PROGRESS OF THIS MONTH (AUG) 25: 8 | STG
| WTB | FAIR FACED FORM | M2 | 617.5 | 0 | 0 | 0 | 0% | 617.5 |  |  | #DIV/0! | [31 empty] | WTB
|  | NORMAL FACED FORM | M2 | 1240.1 | 651 | 8 | 659 | 53.14% | 581.1 |  |  | #DIV/0! | WORK PROGRESS OF THIS MONTH (AUG) 25: 8 | WTB
| FGCB | FAIR FACED FORM | M2 | 588 | 0 | 0 | 0 | 0% | 588 |  |  | #DIV/0! | [31 empty] | FGCB
|  | NORMAL FACED FORM | M2 | 1894.6 | 309.1 | 185 | 494.1 | 26.08% | 1400.5 |  |  | #DIV/0! | WORK PROGRESS OF THIS MONTH (AUG) 7: 50; WORK PROGRESS OF THIS MONTH (AUG) 13: 5; WORK PROGRESS OF THIS MONTH (AUG) 14: 15; WORK PROGRESS OF THIS MONTH (AUG) 15: 20; WORK PROGRESS OF THIS MONTH (AUG) 18: 5; WORK PROGRESS OF THIS MONTH (AUG) 25: 40; WORK PROGRESS OF THIS MONTH (AUG) 26: 30; WORK PROGRESS OF THIS MONTH (AUG) 27: 20 | FGCB
| FGEB | FAIR FACED FORM | M2 | 392 | 0 | 0 | 0 | 0% | 392 |  |  | #DIV/0! | [31 empty] | FGEB
|  | NORMAL FACED FORM | M2 | 1263 | 102.6 | 35 | 137.6 | 10.89% | 1125.4 |  |  | #DIV/0! | WORK PROGRESS OF THIS MONTH (AUG) 8: 3; WORK PROGRESS OF THIS MONTH (AUG) 14: 10; WORK PROGRESS OF THIS MONTH (AUG) 15: 10; WORK PROGRESS OF THIS MONTH (AUG) 19: 10; WORK PROGRESS OF THIS MONTH (AUG) 20: 2 | FGEB
| FWPB | FAIR FACED FORM | M2 | 137.8 | 0 | 0 | 0 | 0% | 137.8 |  |  | #DIV/0! | [31 empty] | FWPB
|  | NORMAL FACED FORM | M2 | 125.6 | 46.24 | 48 | 94.24 | 75.03% | 31.36 |  |  | #DIV/0! | WORK PROGRESS OF THIS MONTH (AUG) 8: 25; WORK PROGRESS OF THIS MONTH (AUG) 22: 5; WORK PROGRESS OF THIS MONTH (AUG) 24: 3; WORK PROGRESS OF THIS MONTH (AUG) 25: 15 | FWPB
| DH S&ACB | FAIR FACED FORM | M2 | 353.9 | 0 | 0 | 0 | 0% | 353.9 |  |  | #DIV/0! | [31 empty] | DH S&ACB
|  | NORMAL FACED FORM | M2 | 642.8 | 146 | 53 | 199 | 30.96% | 443.8 |  |  | #DIV/0! | WORK PROGRESS OF THIS MONTH (AUG) 12: 30; WORK PROGRESS OF THIS MONTH (AUG) 13: 20; WORK PROGRESS OF THIS MONTH (AUG) 25: 1; WORK PROGRESS OF THIS MONTH (AUG) 27: 2 | DH S&ACB
| Calrfied WPB | FAIR FACED FORM | M2 | 216 | 0 | 0 | 0 | 0% | 216 |  |  | #DIV/0! | [31 empty] | Calrfied WPB
|  | NORMAL FACED FORM | M2 | 246.4 | 81.24 | 0 | 81.24 | 32.97% | 165.16 |  |  | #DIV/0! | [31 empty] | Calrfied WPB
| Demi. Pump Building | FAIR FACED FORM | M2 | 286.9 | 0 | 0 | 0 | 0% | 286.9 |  |  | #DIV/0! | [31 empty] | Demi. Pump Building
|  | NORMAL FACED FORM | M2 | 201.2 | 30 | 60 | 90 | 44.73% | 111.2 |  |  | #DIV/0! | WORK PROGRESS OF THIS MONTH (AUG) 7: 30; WORK PROGRESS OF THIS MONTH (AUG) 18: 25; WORK PROGRESS OF THIS MONTH (AUG) 23: 5 | Demi. Pump Building
| Switchyard Control Building | FAIR FACED FORM | M2 | 714 | 0 | 0 | 0 | 0% | 714 |  |  | #DIV/0!
|  | NORMAL FACED FORM | M2 | 393.4 | 0 | 0 | 0 | 0% | 393.4 |  |  | #DIV/0!
| RWPB | FAIR FACED FORM | M2 | 137.8 | 0 | 0 | 0 | 0% | 137.8 |  |  | #DIV/0! | [31 empty] | RWPB
|  | NORMAL FACED FORM | M2 | 125.6 | 65 | 35 | 100 | 79.62% | 125.6 |  |  | #DIV/0! | WORK PROGRESS OF THIS MONTH (AUG) 8: 25; WORK PROGRESS OF THIS MONTH (AUG) 9: 5; WORK PROGRESS OF THIS MONTH (AUG) 10: 5 | RWPB
Rebar Inspection | CEB | HIGH YIELD DEFORMED BAR WORK | ton | 167 | 123.14 | 35 | 158.14 | 94.69% | 8.86 |  |  | #DIV/0! |  |  |  | 2 | 1 | 2 | 3 | 2 | 2 | 3 | 1 | 3 | 3 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 | [5 empty] | CEB
| GTG | HIGH YIELD DEFORMED BAR WORK | ton | 92.4 | 73 | 6 | 79 | 85.5% | 13.4 |  |  | #DIV/0! | WORK PROGRESS OF THIS MONTH (AUG) 3: 1; WORK PROGRESS OF THIS MONTH (AUG) 4: 1; WORK PROGRESS OF THIS MONTH (AUG) 5: 1; WORK PROGRESS OF THIS MONTH (AUG) 16: 1; WORK PROGRESS OF THIS MONTH (AUG) 18: 2 | GTG
| STG | HIGH YIELD DEFORMED BAR WORK | ton | 236 | 78 | 18 | 96 | 40.68% | 140 |  |  | #DIV/0! | WORK PROGRESS OF THIS MONTH (AUG) 5: 1; WORK PROGRESS OF THIS MONTH (AUG) 7: 17 | STG
| Main BLDG | HIGH YIELD DEFORMED BAR WORK | ton | 575.3 | 360.82 | 30 | 390.82 | 67.93% | 184.48 |  |  | #DIV/0! |  |  |  | 1 | 1 | 3 |  | 3 | 3 | 1 | 1 |  | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 |  |  |  |  | Main BLDG
| WTB | HIGH YIELD DEFORMED BAR WORK | ton | 100 | 35 | 0 | 35 | 35% | 65 |  |  | #DIV/0! | [31 empty] | WTB
| FGCB | HIGH YIELD DEFORMED BAR WORK | ton | 133.7 | 38.21 | 9 | 47.21 | 35.31% | 86.49 |  |  | #DIV/0! | WORK PROGRESS OF THIS MONTH (AUG) 4: 1; WORK PROGRESS OF THIS MONTH (AUG) 26: 4; WORK PROGRESS OF THIS MONTH (AUG) 27: 4 | FGCB
| FGEB | HIGH YIELD DEFORMED BAR WORK | ton | 89.1 | 5.78 | 2 | 7.78 | 8.732% | 81.32 |  |  | #DIV/0! | [31 empty] | FGEB | bar: WORK PROGRESS OF THIS MONTH (AUG) 16; WORK PROGRESS OF THIS MONTH (AUG) 20
| FWPB | HIGH YIELD DEFORMED BAR WORK | ton | 12.5 | 4 | 2 | 6 | 48% | 6.5 |  |  | #DIV/0! | [31 empty] | FWPB | bar: WORK PROGRESS OF THIS MONTH (AUG) 22; WORK PROGRESS OF THIS MONTH (AUG) 25
| DH S&ACB | HIGH YIELD DEFORMED BAR WORK | ton | 52.8 | 17 | 6 | 23 | 43.56% | 29.8 |  |  | #DIV/0! | [31 empty] | DH S&ACB | bar: WORK PROGRESS OF THIS MONTH (AUG) 9 to WORK PROGRESS OF THIS MONTH (AUG) 10; WORK PROGRESS OF THIS MONTH (AUG) 18; WORK PROGRESS OF THIS MONTH (AUG) 24; WORK PROGRESS OF THIS MONTH (AUG) 26 to WORK PROGRESS OF THIS MONTH (AUG) 27
| Calrfied WPB | HIGH YIELD DEFORMED BAR WORK | ton | 16.6 | 6 | 1 | 7 | 42.17% | 9.6 |  |  | #DIV/0! | [31 empty] | Calrfied WPB | bar: WORK PROGRESS OF THIS MONTH (AUG) 7
| Demi. Pump Building | HIGH YIELD DEFORMED BAR WORK | ton | 14.8 | 1 | 2 | 3 | 20.27% | 11.8 |  |  | #DIV/0! | WORK PROGRESS OF THIS MONTH (AUG) 6: 2 | Demi. Pump Building
| Switchyard Control Building | HIGH YIELD DEFORMED BAR WORK | ton | 35.8 | 0 | 0 | 0 | 0% | 35.8 |  |  | #DIV/0! | [31 empty] | Switchyard Control Building
| RWPB | HIGH YIELD DEFORMED BAR WORK | ton | 9.9 | 5 | 1 | 6 | 60.61% | 3.9 |  |  | #DIV/0! | [31 empty] | RWPB | bar: WORK PROGRESS OF THIS MONTH (AUG) 8
Back filling | CEB | FOR GENERAL FILL | m3 | 450.3 | 0 | 0 | 0 | 0% | 450.3 |  |  | #DIV/0! | [31 empty] | CEB
|  | FOR STRUCTURAL FILL | m3 | 4052.9 | 3994 | 45 | 4039 | 99.66% | 13.9 |  |  | #DIV/0! | WORK PROGRESS OF THIS MONTH (AUG) 3: 20; WORK PROGRESS OF THIS MONTH (AUG) 4: 10; WORK PROGRESS OF THIS MONTH (AUG) 5: 5; WORK PROGRESS OF THIS MONTH (AUG) 10: 10 | CEB
| Main BLDG | FOR GENERAL FILL | m3 | 1157.4 | 0 | 0 | 0 | 0% | 1157.4 |  |  | #DIV/0! | [31 empty] | Main BLDG
|  | FOR STRUCTURAL FILL | m3 | 10416.5 | 0 | 4850 | 4850 | 46.56% | 5566.5 |  |  | #DIV/0! | [5 empty] | 100 | 200 | 100 | 100 | 100 | 200 | 100 | 200 | 150 | 150 | 200 | 200 | 200 | 200 | 200 | 200 | 250 | 200 | 200 | 700 | 400 | 500 |  |  |  |  | Main BLDG
| WTB | FOR GENERAL FILL | m3 | 269.2 | 0 | 0 | 0 | 0% | 269.2 |  |  | #DIV/0! | [31 empty] | WTB
|  | FOR STRUCTURAL FILL | m3 | 2422.7 | 2374 | 48 | 2422 | 99.97% | 0.7 |  |  | #DIV/0! | WORK PROGRESS OF THIS MONTH (AUG) 25: 20; WORK PROGRESS OF THIS MONTH (AUG) 26: 20; WORK PROGRESS OF THIS MONTH (AUG) 27: 8 | WTB
| FGCB | FOR GENERAL FILL | m3 | 354.1 | 0 | 0 | 0 | 0% | 354.1 |  |  | #DIV/0! | [31 empty] | FGCB
|  | FOR STRUCTURAL FILL | m3 | 3186.9 | 650 | 2200 | 2850 | 89.43% | 336.9 |  |  | #DIV/0! | WORK PROGRESS OF THIS MONTH (AUG) 3: 200; WORK PROGRESS OF THIS MONTH (AUG) 4: 300; WORK PROGRESS OF THIS MONTH (AUG) 5: 400; WORK PROGRESS OF THIS MONTH (AUG) 6: 200; WORK PROGRESS OF THIS MONTH (AUG) 7: 50; WORK PROGRESS OF THIS MONTH (AUG) 8: 50; WORK PROGRESS OF THIS MONTH (AUG) 9: 100; WORK PROGRESS OF THIS MONTH (AUG) 10: 200; WORK PROGRESS OF THIS MONTH (AUG) 13: 150; WORK PROGRESS OF THIS MONTH (AUG) 14: 100; WORK PROGRESS OF THIS MONTH (AUG) 15: 50; WORK PROGRESS OF THIS MONTH (AUG) 16: 50; WORK PROGRESS OF THIS MONTH (AUG) 19: 100; WORK PROGRESS OF THIS MONTH (AUG) 21: 70; WORK PROGRESS OF THIS MONTH (AUG) 22: 50; WORK PROGRESS OF THIS MONTH (AUG) 24: 30; WORK PROGRESS OF THIS MONTH (AUG) 26: 100 | FGCB
| FGEB | FOR GENERAL FILL | m3 | 236.1 | 0 | 0 | 0 | 0% | 236.1 |  |  | #DIV/0! | [31 empty] | FGEB
|  | FOR STRUCTURAL FILL | m3 | 2124.6 | 250 | 300 | 550 | 25.89% | 1574.6 |  |  | #DIV/0! | WORK PROGRESS OF THIS MONTH (AUG) 4: 100; WORK PROGRESS OF THIS MONTH (AUG) 5: 200 | FGEB
| FWPB | FOR GENERAL FILL | m3 | 68.8 | 0 | 0 | 0 | 0% | 68.8 |  |  | #DIV/0! | [31 empty] | FWPB
|  | FOR STRUCTURAL FILL | m3 | 619.1 | 0 | 600 | 600 | 96.91% | 19.1 |  |  | #DIV/0! | WORK PROGRESS OF THIS MONTH (AUG) 12: 100; WORK PROGRESS OF THIS MONTH (AUG) 13: 100; WORK PROGRESS OF THIS MONTH (AUG) 14: 50; WORK PROGRESS OF THIS MONTH (AUG) 15: 50; WORK PROGRESS OF THIS MONTH (AUG) 16: 50; WORK PROGRESS OF THIS MONTH (AUG) 18: 50; WORK PROGRESS OF THIS MONTH (AUG) 19: 50; WORK PROGRESS OF THIS MONTH (AUG) 21: 50; WORK PROGRESS OF THIS MONTH (AUG) 24: 50; WORK PROGRESS OF THIS MONTH (AUG) 25: 30; WORK PROGRESS OF THIS MONTH (AUG) 26: 20 | FWPB
| DH S&ACB | FOR GENERAL FILL | m3 | 158.3 | 0 | 0 | 0 | 0% | 158.3 |  |  | #DIV/0! | [31 empty] | DH S&ACB
|  | FOR STRUCTURAL FILL | m3 | 1425 | 0 | 650 | 650 | 45.61% | 775 |  |  | #DIV/0! | WORK PROGRESS OF THIS MONTH (AUG) 7: 150; WORK PROGRESS OF THIS MONTH (AUG) 8: 150; WORK PROGRESS OF THIS MONTH (AUG) 9: 100; WORK PROGRESS OF THIS MONTH (AUG) 10: 100; WORK PROGRESS OF THIS MONTH (AUG) 24: 50; WORK PROGRESS OF THIS MONTH (AUG) 27: 100 | DH S&ACB
| Calrfied WPB | FOR GENERAL FILL | m3 | 88.5 | 0 | 0 | 0 | 0% | 88.5 |  |  | #DIV/0! | [31 empty] | Calrfied WPB
|  | FOR STRUCTURAL FILL | m3 | 796.5 | 0 | 770 | 770 | 96.67% | 26.5 |  |  | #DIV/0! | WORK PROGRESS OF THIS MONTH (AUG) 7: 150; WORK PROGRESS OF THIS MONTH (AUG) 8: 50; WORK PROGRESS OF THIS MONTH (AUG) 13: 100; WORK PROGRESS OF THIS MONTH (AUG) 14: 50; WORK PROGRESS OF THIS MONTH (AUG) 15: 50; WORK PROGRESS OF THIS MONTH (AUG) 18: 50; WORK PROGRESS OF THIS MONTH (AUG) 19: 50; WORK PROGRESS OF THIS MONTH (AUG) 20: 50; WORK PROGRESS OF THIS MONTH (AUG) 21: 50; WORK PROGRESS OF THIS MONTH (AUG) 22: 50; WORK PROGRESS OF THIS MONTH (AUG) 25: 50; WORK PROGRESS OF THIS MONTH (AUG) 26: 50; WORK PROGRESS OF THIS MONTH (AUG) 27: 20 | Calrfied WPB
| Demi. Pump Building | FOR GENERAL FILL | m3 | 98.6 | 0 | 0 | 0 | 0% | 98.6 |  |  | #DIV/0! | [31 empty] | Demi. Pump Building
|  | FOR STRUCTURAL FILL | m3 | 887.7 | 0 | 200 | 200 | 22.53% | 687.7 |  |  | #DIV/0! | WORK PROGRESS OF THIS MONTH (AUG) 24: 50; WORK PROGRESS OF THIS MONTH (AUG) 27: 150 | Demi. Pump Building
| Switchyard Control Building | FOR GENERAL FILL | m3 | 53.6 | 0 | 0 | 0 | 0% | 53.6 |  |  | #DIV/0!
|  | FOR STRUCTURAL FILL | m3 | 482.2 | 0 | 0 | 0 | 0% | 482.2 |  |  | #DIV/0!
| RWPB | FOR GENERAL FILL | m3 | 54.5 | 0 | 0 | 0 | 0% | 54.5 |  |  | #DIV/0! | [31 empty] | RWPB
|  | FOR STRUCTURAL FILL | m3 | 490.8 | 0 | 430 | 430 | 87.61% | 60.8 |  |  | #DIV/0! | WORK PROGRESS OF THIS MONTH (AUG) 9: 100; WORK PROGRESS OF THIS MONTH (AUG) 10: 50; WORK PROGRESS OF THIS MONTH (AUG) 11: 50; WORK PROGRESS OF THIS MONTH (AUG) 24: 30; WORK PROGRESS OF THIS MONTH (AUG) 26: 100; WORK PROGRESS OF THIS MONTH (AUG) 27: 100 | RWPB
Structural Fill 수급계획 (Borrow Soil)
Carry in Site (A) 반입량 |  | Wagon | m3 | 11839 | 5041 | 1357 | 6398 | 54.04% | 5441 |  |  |  | WORK PROGRESS OF THIS MONTH (AUG) 2: 280; WORK PROGRESS OF THIS MONTH (AUG) 3: 455; WORK PROGRESS OF THIS MONTH (AUG) 8: 280; WORK PROGRESS OF THIS MONTH (AUG) 15: 342
|  | Dump Truck | m3 | 27625 | 3120 | 9060 | 12180 | 44.09% | 15445 |  |  |  | 273 | 560 | 344 | 430 | 455 | 292 | 292 |  | 233 | 175 | 70 | 140 | 210 | 203 | 126 | 266 | 266 | 210 | 343 | 616 | 546 | 546 | 609 | 749 | 413 | 693
|  | Sub-Total | m3 | 39464 | 8161 | 10417 | 18578 | 47.08% | 20886 |  |  |  | 273 | 840 | 799 | 430 | 455 | 292 | 292 | 280 | 233 | 175 | 70 | 140 | 210 | 203 | 468 | 266 | 266 | 210 | 343 | 616 | 546 | 546 | 609 | 749 | 413 | 693 | 0 | 0 | 0 | 0 | 0
Carry out Site (B) 반출량 |  | Sub-Total | m3 | 39464 | 7268 | 10093 | 17361 | 43.99% | 22103 |  |  |  | 0 | 0 | 220 | 410 | 605 | 300 | 550 | 350 | 400 | 460 | 250 | 200 | 550 | 350 | 300 | 300 | 200 | 300 | 400 | 250 | 370 | 350 | 200 | 410 | 800 | 690 | 878 | 0 | 0 | 0 | 0
Difference (A - B) |  | Remain | m3 |  | 893 |  | 1217